## MM_03_13_03
PROJECT MANAGEMENT MEETING MINUTES |  |  |  |  | https://www.smartsheet.com/try-it?trp=11856&utm_source=template-google-sheet&utm_medium=content&utm_campaign=Project+Management+Meeting+Minutes+Sample-google-sheet-11856&lpa=Project+Management+Meeting+Minutes+Sample+google-sheet+11856
1. MEETING DETAILS
DATE | LOCATION | Sequence | START TIME | END TIME
2024-03-13 | USW,Treforest Campus | 3 | 11:30 | 12:15
ATTENDEES
NAME |  | ROLE
Shantanu Shamsundar |  | Project Manager,Public Relations Manager,Technical Member
Mohsen Dianati |  | Technical Manager,Risk Assessor,Technical Member
Nithyashree Thimmegowda |  | Cost Manager,Procurement Manager,Technical Member
Nitharshana Thayanantham |  | Planning Manager,QA Assessor,Technical Member
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Welcomed all attendees and introduced the agenda for the meeting. |  | Mohsen Dianati | 11:30 | 2 Minutes
Discussion of our course work - Deliverable 2 |  | All Members | 11:32 | 7 Minutes
Divide into topics for preparing ppt slides in project communication management |  | All Members | 11:39 | 20 Minutes
Discussion about vedio preparation |  | All Members | 11.59 PM | 6 Minutes
Action Items and Next Steps |  | All Members | 12:06 | 1 Minutes
Upcoming Milestones |  | All Members | 12:07 | 1 Minutes
Meeting Conclusion and Next Meeting Date |  | Nitharshana | 12.10 PM | 3 Minutes
3. PREVIOUS MEETING REVIEW
SUMMARY
Reviewed minutes from the last meeting held on February 25.
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
Item 1 - Review Previous data |  | Nithyashree & Mohsen Dianati | Done
Item 2 - Collect and organize data. |  | Nithyashree & Mohsen Dianati | Done
Item 3 - Listed the Project Communication Headings and Main Titles |  | Nithyashree & Mohsen Dianati | Done
Item 4 - Prepare basic (Level-1) WBS (Work Break Down) |  | Nithyashree & Mohsen Dianati | Done
Item 5 - Prepare meeting minutes for the previous meetings |  | Nitharshana & Shantanu | Done
Item 6 - Prepare organisation chart |  | Nitharshana & Shantanu | Done
4. DISCUSSION POINTS
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Discussion about vedio preparation |  | The Team has discussed about the software for video preparation
Action Items and Next Steps |  | There have been no changes as per the discussions held in previous meetings.
Upcoming Milestones
Meeting Conclusion and Next Meeting Date
5. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE
Item 1 - Prepare ppt Slides |  | All Members | 2024-03-20
Item 2 - Prepare meeting minutes for the previous meetings |  | Nitharshana & Shantanu | 2024-03-20
6. DECISIONS MADE
DECISIONS
After discussion, the Team has decided to prepare narrated video.
7. RISKS AND ISSUES
RISK OR ISSUE |  | MITIGATION PLAN
The risk of relying on personal laptops for our work is compounded by the fact that each team member is located in different places. |  | We have scheduled our meetings to occur every Wednesday following our lectures to discuss important things regarding our projects , with our meetings conducted online. In addition, We've established a folder on Google Drive to centralize our work and share resources collaboratively.
Due to the high volume of tasks at hand, we anticipate that there may be a delay in submission. |  | We adhere to a robust time management system, and as part of our strategy, we aim to complete our coursework 10 days prior to the submission deadline. Our First Submission date is 15.04.2024 but we plan to finished 25.03.2024
8. NEXT STEPS
NEXT STEPS
Confirm Narrated PowerPoint Presentation completion by March 20, for Review
Begin Deliverable 2 – Project Business Justification by March 25
Confirm Project Business Justification completion by April 5, for Review
Begin Deliverable 3 – Joint Reflective Review by April 10
Confirm Joint Reflective Review completion by April 13, for Review
Begin Deliverable 4 – Evidence of Coursework Management by April 15
Confirm Evidence of Coursework Management completion by April 17, for Review
09. UPCOMING MILESTONES
MILESTONES |  | DELIVERABLE DATE
Completion of Deliverable 1 – Narrated PowerPoint Presentation |  | 2024-03-25
Completion of Deliverable 2 – Project Business Justification |  | 2024-04-10
Completion of Deliverable 3 – Joint Reflective Review |  | 2024-04-15
Completion of Deliverable 4 – Evidence of Coursework Management |  | 2024-04-20
10. MEETING CONCLUSION
WRAP-UP
Meeting concluded with a summary of discussions and action items.
DATE OF NEXT MEETING | TIME OF NEXT MEETING | LOCATION OF NEXT MEETING
2024-03-20 | 11.30 PM | USW,Treforest Campus
11. ATTACHMENTS OR SUPPORTING MATERIALS
MATERIALS
https://drive.google.com/drive/folders/1lWanJGtSS1AUms1CRj_bEc1wEjKZk9x5?usp=drive_link
12. APPROVAL AND SIGNATURES
PARTICIPANT NAME |  | SIGNATURE
Shantanu Shamsundar
Mohsen Dianati
Nithyashree Thimmegowda
Nitharshana Thayanantham

## MM_02_09_03
PROJECT MANAGEMENT MEETING MINUTES |  |  |  |  | https://www.smartsheet.com/try-it?trp=11856&utm_source=template-google-sheet&utm_medium=content&utm_campaign=Project+Management+Meeting+Minutes+Sample-google-sheet-11856&lpa=Project+Management+Meeting+Minutes+Sample+google-sheet+11856
1. MEETING DETAILS
DATE | LOCATION | Sequence | START TIME | END TIME
2024-09-03 | Online | 2 | 20:00 | 20:45
ATTENDEES
NAME |  | ROLE
Shantanu Shamsundar |  | Project Manager,Public Relations Manager,Technical Member
Mohsen Dianati |  | Technical Manager,Risk Assessor,Technical Member
Nithyashree Thimmegowda |  | Cost Manager,Procurement Manager,Technical Member
Nitharshana Thayanantham |  | Planning Manager,QA Assessor,Technical Member
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Welcomed all attendees and introduced the agenda for the meeting. |  | Mohsen Dianati | 20:00 | 2 Minutes
Discussion of our course work & identify the main tasks involved in our coursework |  | All Members | 20:02 | 12 Minutes
Discussion about Project Communication Management Topics |  | Nithyashree & Mohsen Dianati | 20:24 | 10 Minutes
Discussion on project management topics applicable for completing our coursework |  | Nitharshana & Shantanu | 8.34 PM | 6 Minutes
Action Items and Next Steps |  | All Members | 20:40 | 1 Minutes
Upcoming Milestones |  | All Members | 20:41 | 1 Minutes
Meeting Conclusion and Next Meeting Date |  | Shantanu | 8.42 PM | 3 Minutes
3. PREVIOUS MEETING REVIEW
SUMMARY
Reviewed minutes from the last meeting held on February 25.
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
Item 1 - Establish a folder on Google Drive to centralize our work and share resources collaboratively. |  | Mohsen Dianati | Done
Item 2 - Outline our coursework plan and identify the main tasks involved in our coursework |  | All Members | Done
Item 3 - List the Project Communication Management Topics |  | Nithyashree & Mohsen Dianati | Done
Item 4 - Collect documents for the meetings and create supporting documents for the coursework. |  | Nitharshana & Shantanu | Done
4. DISCUSSION POINTS
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Discussion on project management topics applicable for completing our coursework |  | The Team has decided to approach this coursework as a project and will adhere to all project management criteria throughout its execution.
Action Items and Next Steps |  | There have been no changes as per the discussions held in previous meetings.
Upcoming Milestones
Meeting Conclusion and Next Meeting Date
5. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE
Item 1 - Review Previous data |  | Nithyashree & Mohsen Dianati | 2024-03-12
Item 2 - Collect and organize data. |  | Nithyashree & Mohsen Dianati | 2024-03-12
Item 3 - Listed the Project Communication Headings and Main Titles |  | Nithyashree & Mohsen Dianati | 2024-03-12
Item 4 - Prepare basic (Level-1) WBS (Work Break Down) |  | Nithyashree & Mohsen Dianati | 2024-03-12
Item 5 - Prepare meeting minutes for the previous meetings |  | Nitharshana & Shantanu | 2024-03-12
Item 6 - Prepare organisation chart |  | Nitharshana & Shantanu | 2024-03-12
6. DECISIONS MADE
DECISIONS
After discussion, the Team has decided to approach this coursework as a project and will adhere to all project management criteria throughout its execution.
7. RISKS AND ISSUES
RISK OR ISSUE |  | MITIGATION PLAN
The risk of relying on personal laptops for our work is compounded by the fact that each team member is located in different places. |  | We have scheduled our meetings to occur every Wednesday following our lectures to discuss important things regarding our projects , with our meetings conducted online. In addition, We've established a folder on Google Drive to centralize our work and share resources collaboratively.
Due to the high volume of tasks at hand, we anticipate that there may be a delay in submission. |  | We adhere to a robust time management system, and as part of our strategy, we aim to complete our coursework 10 days prior to the submission deadline. Our First Submission date is 15.04.2024 but we plan to finished 05.04.2024
8. NEXT STEPS
NEXT STEPS
Confirm Narrated PowerPoint Presentation completion by March 20, for Review
Begin Deliverable 2 – Project Business Justification by March 25
Confirm Project Business Justification completion by April 5, for Review
Begin Deliverable 3 – Joint Reflective Review by April 10
Confirm Joint Reflective Review completion by April 13, for Review
Begin Deliverable 4 – Evidence of Coursework Management by April 15
Confirm Evidence of Coursework Management completion by April 17, for Review
09. UPCOMING MILESTONES
MILESTONES |  | DELIVERABLE DATE
Completion of Deliverable 1 – Narrated PowerPoint Presentation |  | 2024-03-25
Completion of Deliverable 2 – Project Business Justification |  | 2024-04-10
Completion of Deliverable 3 – Joint Reflective Review |  | 2024-04-15
Completion of Deliverable 4 – Evidence of Coursework Management |  | 2024-04-20
10. MEETING CONCLUSION
WRAP-UP
Meeting concluded with a summary of discussions and action items.
DATE OF NEXT MEETING | TIME OF NEXT MEETING | LOCATION OF NEXT MEETING
2024-03-13 | 11.30 AM | USW,Treforest Campus
11. ATTACHMENTS OR SUPPORTING MATERIALS
MATERIALS
https://drive.google.com/drive/folders/1lWanJGtSS1AUms1CRj_bEc1wEjKZk9x5?usp=drive_link
12. APPROVAL AND SIGNATURES
PARTICIPANT NAME |  | SIGNATURE
Shantanu Shamsundar
Mohsen Dianati
Nithyashree Thimmegowda
Nitharshana Thayanantham

## MM_01_25_02
PROJECT MANAGEMENT MEETING MINUTES |  |  |  |  | https://www.smartsheet.com/try-it?trp=11856&utm_source=template-google-sheet&utm_medium=content&utm_campaign=Project+Management+Meeting+Minutes+Sample-google-sheet-11856&lpa=Project+Management+Meeting+Minutes+Sample+google-sheet+11856
1. MEETING DETAILS
DATE | LOCATION | Sequence | START TIME | END TIME
2024-02-25 | Online | 1 | 19:00 | 20:11
ATTENDEES
NAME |  | ROLE
Shantanu Shamsundar |  | Project Manager,Public Relations Manager,Technical Member
Mohsen Dianati |  | Technical Manager,Risk Assessor,Technical Member
Nithyashree Thimmegowda |  | Cost Manager,Procurement Manager,Technical Member
Nitharshana Thayanantham |  | Planning Manager,QA Assessor,Technical Member
2. AGENDA
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
Welcomed all attendees and introduced the agenda for the meeting. |  | Shantanu | 19:00 | 2 Minutes
Discussion of Project Management Topics: Project Procurement Management and Project Communication Management |  | All Members | 19:02 | 15 Minutes
Pros and Cons Analysis about project communication management |  | Shantanu & Mohsen Dianati | 19:17 | 10 Minutes
Pros and Cons Analysis about project procurement management |  | Nithyashree & Nitharshana | 19:27 | 12 Minutes
Selection of Project Management Topic. |  | All Members | 19:39 | 7 Minutes
Reasoning for Selection |  | All Members | 19:46 | 3 Minutes
Action Items and Next Steps |  | All Members | 19:49 | 8 Minutes
Upcoming Milestones |  | All Members | 19:57 | 10 Minutes
Meeting Conclusion and Next Meeting Date |  | Mohsen Dianati | 8.07 PM | 4 Minutes
3. PREVIOUS MEETING REVIEW
SUMMARY
This is the inaugural meeting of our team
4. DISCUSSION POINTS
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
Discussion of Project Management Topics: Project Procurement Management and Project Communication Management |  | The team engaged in a thorough discussion regarding the two proposed project management topics. Each topic was evaluated based on its potential benefits and drawbacks, considering their relevance to our course work objectives and challenges.
Selection of Project Management Topic. |  | After a thorough analysis of the pros and cons of both topics, the team reached a consensus to focus on Project Communication Management.
Reasoning for Selection |  | Given the expansive scope of procurement management compared to project communication management, and considering our constraints on presentation time(18-20 minutes), the team reached a consensus to prioritize project communication management for our discussion.
5. ACTION ITEMS
ACTION ITEM |  | OWNER | DUE DATE
Item 1 - Establish a folder on Google Drive to centralize our work and share resources collaboratively. |  | Mohsen Dianati | 2024-02-26
Item 2 - Outline our coursework plan and identify the main tasks involved in our coursework |  | All Members | 2024-03-07
Item 3 - List the Project Communication Management Topics |  | Nithyashree & Mohsen Dianati | 2024-03-09
Item 4 - Prepare documentation for the meetings and create supporting documents for the coursework. |  | Nitharshana & Shantanu | 2024-03-09
6. DECISIONS MADE
DECISIONS
After discussion, the team decided to focus on the topic of Project Communication Management instead of Project Procurement Management.
7. RISKS AND ISSUES
RISK OR ISSUE |  | MITIGATION PLAN
The risk of relying on personal laptops for our work is compounded by the fact that each team member is located in different places. |  | We have scheduled our meetings to occur every Wednesday following our lectures to discuss important things regarding our projects , with our meetings conducted online. In addition, We've established a folder on Google Drive to centralize our work and share resources collaboratively.
Due to the high volume of tasks at hand, we anticipate that there may be a delay in submission. |  | We adhere to a robust time management system, and as part of our strategy, we aim to complete our coursework 10 days prior to the submission deadline. Our First Submission date is 15.04.2024 but we plan to finished 25.03.2024
8. NEXT STEPS
NEXT STEPS
Confirm Narrated PowerPoint Presentation completion by March 20, for Review
Begin Deliverable 2 – Project Business Justification by March 25
Confirm Project Business Justification completion by April 5, for Review
Begin Deliverable 3 – Joint Reflective Review by April 10
Confirm Joint Reflective Review completion by April 13, for Review
Begin Deliverable 4 – Evidence of Coursework Management by April 15
Confirm Evidence of Coursework Management completion by April 17, for Review
09. UPCOMING MILESTONES
MILESTONES |  | DELIVERABLE DATE
Completion of Deliverable 1 – Narrated PowerPoint Presentation |  | 2024-03-25
Completion of Deliverable 2 – Project Business Justification |  | 2024-04-10
Completion of Deliverable 3 – Joint Reflective Review |  | 2024-04-15
Completion of Deliverable 4 – Evidence of Coursework Management |  | 2024-04-20
10. MEETING CONCLUSION
WRAP-UP
Meeting concluded with a summary of discussions and action items.
DATE OF NEXT MEETING | TIME OF NEXT MEETING | LOCATION OF NEXT MEETING
2024-03-09 | 8.00 PM | Online
11. ATTACHMENTS OR SUPPORTING MATERIALS
MATERIALS
https://drive.google.com/drive/folders/1lWanJGtSS1AUms1CRj_bEc1wEjKZk9x5?usp=drive_link
12. APPROVAL AND SIGNATURES
PARTICIPANT NAME |  | SIGNATURE
Shantanu Shamsundar
Mohsen Dianati
Nithyashree Thimmegowda
Nitharshana Thayanantham

## BLANK Project Mgmt Minutes
PROJECT MANAGEMENT MEETING MINUTES TEMPLATE
1. MEETING DETAILS
DATE | LOCATION |  | START TIME | END TIME
MM/DD/YY
ATTENDEES
NAME |  | ROLE
2. AGENDA
A brief outline of the topics or agenda items for the meeting.
AGENDA ITEMS |  | OWNER / PRESENTED BY | START TIME | DURATION
3. PREVIOUS MEETING REVIEW
A summary of discussions and action items from the previous meeting. Include status updates on action items from the previous meeting.
SUMMARY
ACTION ITEMS AND STATUS UPDATES |  | OWNER / PRESENTED BY | STATUS
4. DISCUSSION POINTS
Include a detailed discussion of each agenda item. Include key points, decisions, and information shared during the discussion. Include any presentations or visuals shared during the meeting.
AGENDA ITEM FOR DISCUSSION |  | DISCUSSION NOTES
5. ACTION ITEMS
List action items and identified during the meeting. Include responsible parties assigned to each item, due dates for each item, and note action items carried forward from previous meetings.
ACTION ITEM |  | OWNER | DUE DATE
6. DECISIONS MADE
Include a clear and concise description of decisions reached during the meeting. Include justifications or context for the decisions, if necessary.
DECISIONS
7. RISKS AND ISSUES
Discuss any new risks or issues identified during the meeting. Include mitigation plans to address these.
RISK OR ISSUE |  | MITIGATION PLAN
8. NEXT STEPS
Summarize key next steps agreed upon in the meeting. Include any follow-up actions or tasks to be taken before the next meeting
NEXT STEPS
9. OTHER BUSINESS
Include any additional items discussed that were not on the original agenda. Add brief descriptions and outcomes of those discussions.
ADDITIONAL ITEMS | DESCRIPTION |  | OUTCOMES
10. UPCOMING MILESTONES
Include reminders of important project milestones, deadlines, or events.
MILESTONES
11. MEETING CONCLUSION
Note a brief wrap-up of the meeting discussions. Confirm the date, time, and location of the next meeting. Note any materials to be distributed before the next meeting.
WRAP-UP
DATE OF NEXT MEETING | LOCATION OF NEXT MEETING
12. ATTACHMENTS OR SUPPORTING MATERIALS
Link or attach relevant documents, presentations, or reports discussed during the meeting.
MATERIALS
13. APPROVAL AND SIGNATURES
Sign below to approve meeting minutes.
PARTICIPANT NAME |  | SIGNATURE